## Issue List
# | Severity | Issue | Fix | Status | Summary
1 | Critical | Week 3 README/report claims PKR 6,750,000 revenue across 8,500 rides (avg PKR 794.12). Real data: $31,788.97 across 50 rides, in USD. | Delete/rewrite every PKR, 8,500 and 794.12 figure. | Open | Critical | 5
2 | Critical | README says PayPal is top payment method and SUV top vehicle type. Real: Visa top ($9,297); Bus ($9,757) and Sedan ($9,632) top vehicle types; PayPal last ($4,029). | Rewrite findings and recommendations built on them. | Open | High | 3
3 | Critical | README says December is peak revenue month. Real peak is June 2022 ($3,109.66); all Decembers total $2,913.19; no seasonal pattern. | Remove seasonality claim and December recommendation. | Open | Medium | 2
4 | Critical | README names Driver JC9570 (high cancellation), CX2751 (top revenue), hotspot 19.013028,68.535171. Real: 0 cancellations; top-revenue driver is OC1811 ($1,159.06); every pickup location is unique. | Remove or replace these claims. | Open | Low | 1
5 | Critical | Week 4 screenshot showed Total Rides 650, Cancelled 600, Completion Rate 0.08 (fan-out bug). | Confirm via fresh screenshot that cards read 50 / 0 / 100%. | Open | Open | 11
6 | High | Ride distances range 525 to 12,132 miles (median 6,374) - impossible for ride-hailing. Brief requires checking impossible distances. | Document as data-quality finding; caveat distance-based insights ($0.103/mile rate, Motorcycle longest trips). | Open | Resolved | 0
7 | High | Week 5 insight 9 says "zero missing Customer IDs"; no Customer ID column exists. | Reword to "no Customer ID field exists". | Open
8 | High | Week 2 README claims customer, new-vs-repeat and weekday/weekend analysis the data cannot support. | Add documented-limitation wording. | Open
9 | Medium | Inconsistent table names (Ride_Sharing_Dataset vs _FIXED); Request Time chart built as a bar list. | Rename tables consistently; use a line chart. | Open
10 | Medium | Ride Status derived from Fare = 0 (circular proxy, not real status data). | State in methodology notes. | Open
11 | Low | Duplicated logic: raw Completion Rate (%) column in driver file vs DAX Completion Rate measure. | Keep one source of truth for each; label the other. | Open

## Verified Figures
Metric | Value | Note
Total rides | 50 | Ride_Sharing_Dataset.csv
Total revenue ($) | 31788.97 | Sum of Fare Amount (in $)
Cancelled rides | 0 | No fares of $0
Peak revenue month | 2022-06 | $3,109.66
December revenue, all years ($) | 2913.19 | Not the peak
Top payment method | Visa | $9,297.30
Top vehicle types | Bus / Sedan | $9,756.79 / $9,631.78
Top-revenue driver | OC1811 | $1,159.06
Distance min-max (miles) | 525 - 12,132 | Implausible
Average rating | 2.80 / 5 | 23 of 50 rides rated 1-2 stars

## Consistent Story
Final story the data supports
A small ride dataset: $31.8K revenue from 50 completed rides at about $636 per ride.
Revenue is concentrated in Sedan and Bus and in Visa and Debit Card payments.
Ratings are low (2.80/5) despite 100% completion.
Data gaps (no customers, cancellations or realistic distances) limit deeper analysis.